## Sheet2
Description | Start date | End date | Working Days
Preparation & Process Management
Document Creation / Re;ease Schedule
Notify Initial seven (7) Bidding Entities on Pending RFP Release & Schedule | 2025-02-28 | 2025-02-28 | 1
HIMSS 2025, Las Vegas, NV - Final Determination of Bidding Entities | 2025-03-03 | 2025-03-06 | 4
Vancouver Clinic Document Sign-Off for Release of RFP | 2025-03-11 | 2025-03-12 | 2
RFP Released to Bidding Entities and Direct Communication | 2025-03-12 | 2025-03-12 | 1
Bid Response Management
Formal questions period (in writing) | 2025-03-12 | 2025-03-24 | 9
Bidders prepare RFP Responses | 2025-03-12 | 2025-04-02 | 16
RFP Kick-Off Call with Bidding Entities | 2025-03-14 | 2025-03-14 | 1
Notifications of “Intent” due | 2025-03-17 | 2025-03-17 | 1
Bidding Entity 1 Conference | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 2 Conference | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 3 Conference | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 4 Conference | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 5 Conference | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 6 Conference | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 7 Conference | 2025-03-20 | 2025-03-20 | 1
Release of Addendum to RFP (if necessary) | 2025-03-24 | 2025-03-24 | 1
Open Conference Call ¦ Addendum to RFP | 2025-03-26 | 2025-03-26 | 1
RFP Responses Due / Categorized and Distributed | 2025-04-03 | 2025-04-03 | 1
Reviews, Presentations, and Demonstrations
Review & Scoring
Vancouver Clinic reviews RFP Responses | 2025-04-04 | 2025-04-10 | 5
Scoring Review and Presenter Selection | 2025-04-11 | 2025-04-11 | 1
Notification to Presenters | 2025-04-11 | 2025-04-11 | 1
Scheduling for Onsite Presentation Visits by Vancouver Clinic | 2025-04-11 | 2025-04-11 | 1
Passover (Jewish Holidays) | 2025-04-12 | 2025-04-20 | 5
Easter Sunday | 2025-04-20 | 2025-04-20 | 0
Executive / Sales Presentations (Not for Demonstations)
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demonstrations ¦ Radiology
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demonstrations ¦ Mammography / Women's Imaging
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demionstrations ¦ Cardiology
Presenting Entity 1 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 Presentation | 2025-04-21 | 2025-04-25 | 5
Final Selection
Vancouver Clinic conducts final internal reviews | 2025-04-30 23:59 | 2025-04-30 23:59 | 1
Vancouver Clinic I H-I-S Notifies Bidder moving to Contract | 2025-05-01 23:59 | 2025-05-01 23:59 | 1
Contracting Process Conducted by Vancouver Clinic I H-I-S Program Complete | 2025-05-01 23:59 | 2025-05-01 23:59 | 1
Updated March 12, 2025
Formulas:
Working Days = NETWORKDAYS(Table1[[#This Row],[Start date]],Table1[[#This Row],[End date]])

## Named Bidding Entities
Description | Start date | End date | Working Days
Preparation & Process Management
Document Creation / Re;ease Schedule
Notify Initial seven (7) Bidding Entities on Pending RFP Release & Schedule | 2025-02-28 | 2025-02-28 | 1
HIMSS 2025, Las Vegas, NV - Final Determination of Bidding Entities | 2025-03-03 | 2025-03-06 | 4
Vancouver Clinic Document Sign-Off for Release of RFP | 2025-03-11 | 2025-03-12 | 2
RFP Released to Bidding Entities and Direct Communication | 2025-03-12 | 2025-03-12 | 1
Bid Response Management
Formal questions period (in writing) | 2025-03-12 | 2025-03-24 | 9
Bidders prepare RFP Responses | 2025-03-12 | 2025-04-02 | 16
RFP Kick-Off Call with Bidding Entities | 2025-03-14 | 2025-03-14 | 1
Notifications of “Intent” due | 2025-03-17 | 2025-03-17 | 1
Bidding Entity 1 Conference (Merge) | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 2 Conference (Optum) | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 3 Conference (GE) | 2025-03-18 | 2025-03-18 | 1
Bidding Entity 4 Conference (Intelerad) | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 5 Conference (Sectra) | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 6 Conference (Fuji) | 2025-03-19 | 2025-03-19 | 1
Bidding Entity 7 Conference (Visage) | 2025-03-20 | 2025-03-20 | 1
Release of Addendum to RFP (if necessary) | 2025-03-24 | 2025-03-24 | 1
Open Conference Call ¦ Addendum to RFP | 2025-03-26 | 2025-03-26 | 1
RFP Responses Due / Categorized and Distributed | 2025-04-03 | 2025-04-03 | 1
Reviews, Presentations, and Demonstrations
Review & Scoring
Vancouver Clinic reviews RFP Responses | 2025-04-04 | 2025-04-10 | 5
Scoring Review and Presenter Selection | 2025-04-11 | 2025-04-11 | 1
Notification to Presenters | 2025-04-11 | 2025-04-11 | 1
Scheduling for Onsite Presentation Visits by Vancouver Clinic | 2025-04-11 | 2025-04-11 | 1
Passover (Jewish Holidays) | 2025-04-12 | 2025-04-20 | 5
Easter Sunday | 2025-04-20 | 2025-04-20 | 0
Executive / Sales Presentations (Not for Demonstations)
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demonstrations ¦ Radiology
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demonstrations ¦ Mammography / Women's Imaging
Presenting Entity 1 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 | 2025-04-21 | 2025-04-25 | 5
Clinical Reviews / Demionstrations ¦ Cardiology
Presenting Entity 1 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 2 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 3 Presentation | 2025-04-21 | 2025-04-25 | 5
Presenting Entity 4 Presentation | 2025-04-21 | 2025-04-25 | 5
Final Selection
Vancouver Clinic conducts final internal reviews | 2025-04-30 23:59 | 2025-04-30 23:59 | 1
Vancouver Clinic I H-I-S Notifies Bidder moving to Contract | 2025-05-01 23:59 | 2025-05-01 23:59 | 1
Contracting Process Conducted by Vancouver Clinic I H-I-S Program Complete | 2025-05-01 23:59 | 2025-05-01 23:59 | 1
Updated March 12, 2025
Formulas:
Working Days = NETWORKDAYS(Table13[[#This Row],[Start date]],Table13[[#This Row],[End date]])